## Sheet1
task_id | task_name | module | mail_id | product_owner | assigned_to | duration_days | start_date | end_date | completion_percent | status | dependencies | risk_level | risk_reason
1 | EIP Templates to be shared with client | Employee Information Portal | adarsh.arvr@gmail.com | Nihar | adarsh.arvr@gmail.com | 1 | 2025-12-25 | 2025-12-26 | 0 | Completed | nan | on_track | Not due this month
2 | Explanation of EIP templates | General | adarshprvt@gmail.com | Adarsh | adarshprvt@gmail.com | 1 | 2025-12-07 | 2025-12-08 | 20 | Completed | nan | on_track | Not due this month
3 | Client to send completed EIP Master templates | General | adarsh.arvr@gmail.com | Adarsh | adarsh.arvr@gmail.com | 3 | 2025-11-03 | 2025-11-06 | 0 | Pending | nan | on_track | On schedule, 0% complete
4 | Data validation of the master data, workflows | General | adarshprvt@gmail.com | Nihar | adarshprvt@gmail.com | 2 | 2025-10-18 | 2025-10-20 | 100 | In Progress | nan | on_track | Completed: 100%
5 | Master set up from Account Activation Template Shared by client | General | adarsh.arvr@gmail.com | Adarsh | adarsh.arvr@gmail.com | 2 | 2025-12-19 | 2025-12-21 | 50 | In Progress | nan | on_track | Not due this month
6 | Configuration of Master set up from Account Activation Template | General | adarshprvt@gmail.com | Nihar | adarshprvt@gmail.com | 3 | 2025-11-28 | 2025-12-01 | 40 | In Progress | nan | on_track | Not due this month
7 | Client to send filled confirmation policy setup,HR user rights and asset rights templates | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-10-28 | 2025-10-30 | 100 | Pending | nan | on_track | Completed: 100%
8 | Configuration of confirmation policy setup,HR user rights | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 3 | 2025-10-20 | 2025-10-23 | 100 | In Progress | nan | on_track | Completed: 100%
9 | Define and activate notifications/escalations | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-15 | 2025-12-16 | 20 | In Progress | nan | on_track | Not due this month
10 | Client to send employee data | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-12-01 | 2025-12-03 | 0 | Pending | nan | on_track | Not due this month
11 | Validation of employee records templates as per the EW System | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 3 | 2025-12-24 | 2025-12-27 | 10 | Delayed | nan | on_track | Not due this month
12 | Upload employee records | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-10-25 | 2025-10-27 | 100 | On Hold | nan | on_track | Completed: 100%
13 | User Acceptance Testing | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 3 | 2025-10-27 | 2025-10-30 | 100 | In Progress | nan | on_track | Completed: 100%
14 | Intergation Activities | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 7 | 2025-11-20 | 2025-11-27 | 20 | In Progress | nan | at_risk | Due Nov 27, progress: 20%
15 | Integration UAT | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-11-01 | 2025-11-03 | 100 | Pending | nan | on_track | Completed: 100%
16 | Train the Trainer | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-10 | 2025-11-11 | 20 | Completed | nan | on_track | On schedule, 20% complete
17 | Module Go-live | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-12 | 2025-12-13 | 40 | Pending | nan | on_track | Not due this month
18 | L&A templates to be shared with client | L&A Module | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-09 | 2025-12-10 | 0 | Completed | nan | on_track | Not due this month
19 | Explanation of leave rules templates, leave balance & attendance templates | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-22 | 2025-11-23 | 70 | Pending | nan | on_track | On schedule, 70% complete
20 | Client to send completed leave rules templates | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-15 | 2025-11-16 | 70 | Pending | nan | on_track | On schedule, 70% complete
21 | Client to send Leave balance & Transactions ( if any) | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 3 | 2025-12-13 | 2025-12-16 | 20 | In Progress | nan | on_track | Not due this month
22 | Client to send Shift Master Template | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-03 | 2025-12-04 | 50 | Pending | nan | on_track | Not due this month
23 | Client to send Actual Roster and Attendance in EW template (Attendance Data) | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-12-16 | 2025-12-18 | 60 | In Progress | nan | on_track | Not due this month
24 | Validation of leave rules sent by client | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-22 | 2025-12-23 | 30 | Delayed | nan | on_track | Not due this month
25 | Validation of Leave and Attendance, Data, Workflow | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-11-07 | 2025-11-09 | 20 | Delayed | nan | on_track | On schedule, 20% complete
26 | Leave module set-up (Leave rules, leave types and holidays) | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-11-05 | 2025-11-07 | 40 | In Progress | nan | on_track | On schedule, 40% complete
27 | Confiuration and Data Migration of Leave | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-10-11 | 2025-10-13 | 100 | Pending | nan | on_track | Completed: 100%
28 | Configuration of notification/alerts and escalations | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-20 | 2025-11-21 | 10 | Pending | nan | alert | Due in 5 days (Nov 21), only 10% complete
29 | Attendance module set up( Shift and shift Pattern, OD, PA etc) | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-11-23 | 2025-11-25 | 40 | Pending | nan | at_risk | Due Nov 25, progress: 40%
30 | First time roster upload | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-12 | 2025-11-13 | 60 | Pending | nan | on_track | On schedule, 60% complete
31 | Attendance upload | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 4 | 2025-12-19 | 2025-12-23 | 70 | Pending | nan | on_track | Not due this month
32 | Share database for biometrics integration | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-15 | 2025-12-16 | 10 | Pending | nan | on_track | Not due this month
33 | Configure and test the IP based attendance( Integration with Biometrics) | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-29 | 2025-11-30 | 70 | Delayed | nan | on_track | On schedule, 70% complete
34 | Validation of configuration Leave and Attendance, Data, Workflow set up | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-11-16 | 2025-11-18 | 50 | Delayed | nan | on_track | On schedule, 50% complete
35 | Conduct Train-the trainer | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-06 | 2025-11-07 | 60 | Delayed | nan | on_track | On schedule, 60% complete
36 | User Acceptance Testing | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-11-22 | 2025-11-24 | 40 | In Progress | nan | at_risk | Due Nov 24, progress: 40%
37 | Module Go-Live | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-10-22 | 2025-10-23 | 100 | Pending | nan | on_track | Completed: 100%
38 | ES templates to be shared with client | Employee Separation Module | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-17 | 2025-11-18 | 10 | Completed | nan | alert | Due in 2 days (Nov 18), only 10% complete
39 | Explanation of ES templates | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-10-27 | 2025-10-28 | 100 | Delayed | nan | on_track | Completed: 100%
40 | Client to send Separation Workflow, Rules, process in ES templates | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-10 | 2025-11-11 | 10 | Pending | nan | on_track | On schedule, 10% complete
41 | Client to send Clearances item, Workflow, process in ES templates | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-26 | 2025-12-27 | 60 | Completed | nan | on_track | Not due this month
42 | Client to send Exit interview feedback form | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-12-23 | 2025-12-24 | 70 | In Progress | nan | on_track | Not due this month
43 | Validation of ES rules & exit Feedback form sent by client, Validation of Clearances item, Workflow, process | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-10-24 | 2025-10-25 | 100 | On Hold | nan | on_track | Completed: 100%
44 | Configuration and Data Migration for ES | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 3 | 2025-12-16 | 2025-12-19 | 40 | Completed | nan | on_track | Not due this month
45 | Configuration of notification/alerts and escalations | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-04 | 2025-11-05 | 40 | In Progress | nan | on_track | On schedule, 40% complete
46 | Validation of Separation configuration, Data, Workflow set up | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-10-20 | 2025-10-22 | 100 | Pending | nan | on_track | Completed: 100%
47 | Conduct Train-the trainer | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-15 | 2025-11-16 | 60 | Pending | nan | on_track | On schedule, 60% complete
48 | User Acceptance Testing | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-11-30 | 2025-12-02 | 60 | In Progress | nan | on_track | Not due this month
49 | Module Go-Live | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-15 | 2025-11-16 | 50 | In Progress | nan | on_track | On schedule, 50% complete
50 | Explanation of C&B templates | Compensation & Benefits Module | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-16 | 2025-11-17 | 40 | Pending | nan | on_track | On schedule, 40% complete
51 | Payhead, salary benefit and payroll policy to be sent by client in C&B templates | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-28 | 2025-11-29 | 40 | In Progress | nan | at_risk | Due Nov 29, progress: 40%
52 | Employee Compensation data to be sent by client in C&B template | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-16 | 2025-11-17 | 70 | Completed | nan | on_track | On schedule, 70% complete
53 | Validation of payheads and compensation data | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-09 | 2025-12-10 | 0 | Pending | nan | on_track | Not due this month
54 | Start Statutory Employer configuration | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-12-08 | 2025-12-09 | 60 | Completed | nan | on_track | Not due this month
55 | Create payroll rule in case payroll is to be run for the implementaiton is compulsory . Once payroll rule is created start configuration of Pay heads. | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-04 | 2025-12-05 | 50 | Completed | nan | on_track | Not due this month
56 | Upload of Employee Compensation data | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 3 | 2025-11-04 | 2025-11-07 | 40 | Delayed | nan | on_track | On schedule, 40% complete
57 | Compensation Data Checking and Validation | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-10 | 2025-11-11 | 70 | On Hold | nan | on_track | On schedule, 70% complete
58 | Upload of statutory details of employees | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-12-18 | 2025-12-19 | 70 | In Progress | nan | on_track | Not due this month
59 | Client employeees to fill Tax Declaration Data on EW | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 3 | 2025-11-08 | 2025-11-11 | 15 | In Progress | nan | on_track | On schedule, 15% complete
60 | Validate payheads, salary benefit and employee compensation data | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-11-05 | 2025-11-06 | 15 | Completed | nan | on_track | On schedule, 15% complete
61 | Conduct Train-the trainer | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-06 | 2025-11-07 | 15 | Completed | nan | on_track | On schedule, 15% complete
62 | User Acceptance Testing | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-10-21 | 2025-10-22 | 100 | In Progress | nan | on_track | Completed: 100%
63 | Module Go-Live | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-07 | 2025-11-08 | 40 | In Progress | nan | on_track | On schedule, 40% complete
64 | Client to share paysheets and Paid days for each month from April to September | Payroll & Taxation | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-12-11 | 2025-12-13 | 20 | Completed | nan | on_track | Not due this month
65 | EW to verify the settings related to payroll & taxation | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-10-28 | 2025-10-29 | 100 | In Progress | nan | on_track | Completed: 100%
66 | Paysheet data validation for April,May, June, July | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-11-08 | 2025-11-09 | 20 | Delayed | nan | on_track | On schedule, 20% complete
67 | Client to verify and validate system generated April paysheet | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 2 | 2025-12-14 | 2025-12-16 | 60 | In Progress | nan | on_track | Not due this month
68 | Client to verify and validate system generated May paysheet | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-12-20 | 2025-12-22 | 0 | Completed | nan | on_track | Not due this month
69 | Client to verify and validate system generated June paysheet | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-11-16 | 2025-11-18 | 10 | AUTO-REALLOCATED to adarsh.arvr@gmail.com | nan | alert | Due in 2 days (Nov 18), only 10% complete
70 | Client to verify and validate system generated June paysheet | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 2 | 2025-12-07 | 2025-12-09 | 70 | Completed | nan | on_track | Not due this month
71 | Train the trainer | General | adarshprvt@gmail.com | nan | adarshprvt@gmail.com | 1 | 2025-10-19 | 2025-10-20 | 100 | In Progress | nan | on_track | Completed: 100%
72 | Module Go-Live | General | adarsh.arvr@gmail.com | nan | adarsh.arvr@gmail.com | 1 | 2025-12-10 | 2025-12-11 | 10 | In Progress | nan | on_track | Not due this month